## Gantt Chart
GANTT CHART
PROJECT TITLE |  | 306 Project one |  |  |  |  | COMPANY NAME | [8 empty] | Group 15
PROJECT MANAGER |  | Eugene Bulog |  |  |  |  | DATE | [8 empty] | 2018-07-24
WBS NUMBER | TASK TITLE | TASK ASSIGNMENT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Milestone 1 | [14 empty] | MILESTONE TWO
[7 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
1 | Project Definition and Planning |  | 2018-07-26 | 2018-07-31 | 5 |  | WEEK 2 T: 26; WEEK 2 F: 27; WEEK 2 S: 28; WEEK 2 S: 29; WEEK 3 M: 30; WEEK 3 T: 31
1.1 | Requirements | HS, MF | 2018-07-26 | 2018-07-26 | 1 | 0% | bar: WEEK 2 T
1.2 | Limitations | HS, MF | 2018-07-27 | 2018-07-27 | 1 | 0% | bar: WEEK 2 F
1.3 | A* and DFS algorithms research | EB, ND, SB | 2018-07-26 | 2018-07-27 | 2 | 0% | bar: WEEK 2 T to WEEK 2 F
1.4 | A* and DFS algorithms comparison | ND,MF | 2018-07-28 | 2018-07-29 | 2 | 0% | bar: WEEK 2 S to WEEK 2 S
1.5 | Possible tweaks to algorithms | EB, SB | 2018-07-28 | 2018-07-29 | 2 | 0% | bar: WEEK 2 S to WEEK 2 S
1.6 | List of useful frameworks/APIs/Libraries | EB, ND, SB, MF | 2018-07-30 | 2018-07-30 | 1 | 0% | bar: WEEK 3 M
1.7 | Class structure & planning | EB,MF | 2018-07-31 | 2018-07-31 | 1 | 0% | bar: WEEK 3 T
2 | Prototyping |  | 2018-07-31 | 2018-08-02 | 2 |  | WEEK 3 T: 31; WEEK 3 W: 1; WEEK 3 T: 2
2.1 | Toy algorithm implementation | ND,SB | 2018-07-31 | 2018-08-01 | 2 | 0% | bar: WEEK 3 T to WEEK 3 W
2.2 | Toy algorithm comparison & selection | ND,SB | 2018-08-02 | 2018-08-02 | 1 | 0% | bar: WEEK 3 T
3 | Development |  | 2018-08-02 | 2018-08-09 | 7 | [11 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
3.1 | Input Parsing | EB, MF, HS | 2018-07-02 | 2018-07-03 | 2 | 0% | bar: 2 to 3
3.2 | Inital algorithm implementation | ALL | 2018-08-04 | 2018-08-05 | 2 | 0% | bar: 4 to 5
3.3 | GUI implemenation | ND | 2018-08-07 | 2018-08-09 | 3 | 0% | bar: 7 to 9
4 | Testing |  | 2018-07-28 | 2018-08-19 | 22 | [6 empty] | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
4.1 | Unit test definitions | HS | 2018-07-28 | 2018-07-30 | 3 | 0% | bar: 28 to 30
4.2 | Unit test implementation | HS | 2018-07-31 | 2018-08-01 | 2 | 0% | bar: 31 to 1
4.3 | Unit test analysis | SB | 2018-08-07 | 2018-08-18 | 12 | 0% | bar: 7 to 18
4.4 | Lab computer test | HS | 2018-08-19 | 2018-08-19 | 1 | 0% | bar: 19
4.5 | Multiple OS test | MF | 2018-08-19 | 2018-08-19 | 1 | 0% | bar: 19
5 | Refinement |  | 2018-08-07 | 2018-08-18 | 11 | [16 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
5.1 | Improved/optimised algorithm | MF,ND | 2018-08-07 | 2018-08-18 | 12 | 0%
5.2 | Bug Fixes | EB,HS | 2018-08-07 | 2018-08-18 | 12 | 0%
6 | Documenting |  | 2018-08-06 | 2018-08-24 | 18 | [15 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
6.2 | First interview prep | All | 2018-08-06 | 2018-08-06 | 1 | 0%
6.1 | User documentation | MF,ND | 2018-08-07 | 2018-08-18 | 12 | 0% | bar: 6 to 18
6.3 | Demo & second interview prep | All | 2018-08-19 | 2018-08-20 | 2 | 0% | bar: 19 to 20
6.4 | Final report | All | 2018-08-20 | 2018-08-24 | 5 | 0% | bar: 20 to 24
Formulas:
DURATION = DATEDIF([START DATE],[DUE DATE],"d")
DURATION = DATEDIF([START DATE],[DUE DATE],"D") + 1